## Action Items
Task | Responsible | Status | Priority | Completion | Description | Notes | Last Updated Date | Deadline
Buy More Magnets, Power Supply | Jake, Rence, Chris | Complete | High | 100% | Buy Magnets for the Physical and Projected Globe | 4/13/17 - Interaction Controls powers are purchased. Waiting on the power level for Levitation Supply 4/17/17 - Chris says hold off because we can use lab equipment | 2017-04-17 | 2017-03-20
Base Product Design | Kevin | Complete | Low | 100% | Designing the outer Base for the Globe | 4/13/17 - Kevin has designed the Base in Solidworks. Printed out the Gesture Control Base 4/28/17 - Just need to print out the body for the PCB | 2017-04-28 | 2017-04-21
Research Power Supplies | Kevin, Jake | Complete | Low | 100% | Research Buck Converter for your device, maximum current draw and voltage:ask for whoever is working with a device that needs power | 4/13/17 -Kevin's Interaction Controls power supply is purchased | 2017-04-13 | 2017-04-13
Research Code Capadibility with PIC24, H-Bridge and Hall-effect Sensors | Chris, Mark, Jake | Complete | High | 100% | sampling, ADC values and ranges, PWM speed and speed of switching of H-bridge with multiple deadband specs, current sensing, thermo protection | 4/13/17 - Found an online thesis where we can base our design and code on | 2017-04-13 | 2017-04-09
Design PCB Board | Andres | Complete | High | 100% | Boards for the H-Bridges & Hall Effect Sensors | 4/13/17 - Have rough sketch of how the PCB will layed out 4/15/17 - Bottom PCB for the Base Magnet is almost finished | 2017-04-15 | 2017-04-14
Validate ADC Works | Mark | Complete | High | 100% | The Clocking rate of the ADC must be in the correct range, in order to get the correct output | 4/15/17 - Slowed down the Sampling rate, now the ADC is accurate | 2017-04-15 | 2017-04-17
Calcualate the physical forces affecting the levitation | Chris, Rence | Complete | Medium | 100% | Understanding the calculatoins done in the Levitation Thesis | 4/15/17 - Recorded the Dipole Measurements from the Base Magnet. Need to figure out the rest of the calculations and how it relates to the PID controls. | 2017-04-15 | 2017-04-19
PID Controls System | Brian,Mark | Assigned | High | 80% | Writing the PID Controls System and fine tuning the values to get the magnet to become stable | 4/15/17 - Psuedo code is written waiting on PCB to get actual readings 5/3/17 - PI is wirtten and semi levitation is produced. | 2017-05-03 | 2017-04-25
Project Poster | Rence | Complete | Low | 100% | Design the layout for the final Project Poster and get it printed out | 4/15/17 - Have the Dimensions of the Poster | 2017-04-15 | 2017-04-25
Update the Website | Brian | Complete | Low | 100% | Add more content to the website, such as pictures, flow charts, the progress, and logic | 4/15/17 - Website has basic content. | 2017-04-15 | 2017-04-30
Final Presentation Powerpoint Layout | Rence | Complete | Low | 100% | Make the Final Presnetation fresh and clean | 4/15/17 - Start | 2017-04-15 | 2017-04-20
Budget Analytics | Jake | Complete | Low | 100% | Create a budget analysis for Overall budget and acutal cost of finish product | 4/15/17-Assigned 5/3/17 - Finished | 2017-05-03 | 2017-04-25
Rotataion Mechanics | Leon | Complete | Low | 100% | Design the gears and mechanics to how the globe will rotate, as well as the tranciever communication | 4/15/17 - Start 5/3/17 - Rotating with a DC Motor | 2017-05-03 | 2017-04-25

## Archive
Task | Responsible | Status | Priority | Completion | Description | Notes | Last Updated Date | Deadline
Projecting the Map onto the Globe | Andres, Leon, Brian | Complete | High | 100% | Projecting the map onto the Globe | Going the Physical Globe route and Projection Route | 2017-03-23
Map GUI Aesthetics & Information | Leon | Complete | Medium | 100% | Construct an interactive QGIS Map, that becomes intergrated with the voice, gesture, and database | 3/23/17 - Done with Base Design | 2017-03-23 | 2017-03-17
Map GUI Scripting | Mark | Complete | Medium | 100% | Python Scripting to control the Map. Will be interfaced with the voice and gesture recognition commands | Moving away from QGIS. Converted to Google Maps | 2017-03-14
Database API | Brian | Complete | High | 100% | Pull and parse data from an online data source and integrate the Database with voice and map commands | Cities & States are confused, need to reconstruct the database | 2017-04-13 | 2017-03-24
Voice & Gesture Recognition | Kevin, Brian | Complete | Medium | 100% | An API that will read Voice and Gestures and integrate it with the map scripting | Expereiment with materials | 2017-04-13 | 2017-04-07
Reviewing a pre-existing Levitation Device | Rence, Jake | Complete | High | 100% | Studying and analyzing a levitating device and use that build as a reference point | 4/13/17 - Need to get the readings | 2017-04-13
Drawing Levitating Schematics from Pre-existing Device | Rence | Unfinished | High | 100% | Reverse Engineering Pre-Existing Levitating Device | 3/14/17 -Need to add the capictors - Schematic is missing labels | 2017-03-14
Calculations | Chris | Unfinished | High | 50% | Calculate the circuit design necssary for levitating device from the top or bottom | 3/14/17 - Abandoned!!!! | 2017-03-14
Hall-Effect Sensors | Jake | Complete | Medium | 100% | Learn and understand how the sensors work and how it will utilzied in the levitation process | 3/14/17 - Waiting for parts. Know what it is ready 4/13/17 - Recieved, and putting 4 Sensors on the top of the magnet | 2017-04-13
Buying microcontroller | Andres, Leon | Complete | Medium | 100% | Finding microcontroller to introduce levitation feedback system | 3/23/17 - Buying ones in the dip package | 2017-03-23
Purchasing and Testing the Sensors | Rence, Jake | Complete | High | 30% | Purchase Sensors and start testing and recording the values from the sensors | 3/14/17 - Ordered 4/13-17 - Purchased & Sensors readings recorded for different positions & Distance | 2017-04-13 | 2017-03-24
Inductive Power Transfer | Andres, Brian | Complete | Low | 100% | Wirless Power for the motor inside the Physical Globe | 3/23/17 - Bought Kit, need to buy HBridge 4/13/17 - Abandoned b/c power is to low for required distance | 2017-04-13 | 2017-03-21
PID Motor Control | Leon, Mark, Brian | Hold | Low | 0% | Rotates the Globe while also keeping it stable | 3/14/17 - Haven't started 4/13/17 - On hold focusing on Levitation | 2017-04-13 | 2017-04-06
Integrate GUI with Data API | Leon, Mark, Brian | Complete | Medium | 100% | Need to dynamically update the html page with the data from the database. | Need to Implement Commands | 2017-03-23 | 2017-03-21
Finalizing Schematic | Jake, Rence, Chris | Unfinished | High | 80% | Finalize levitation schematic | 3/23/17 - Need to incorporate optimal sensors in the design. Need to test between IR sensor 4/13/17 - Schematic is being constructed onto a PCB by Andres, specifically just connecting H-Bridges to control the current from the Coils, and Hall Effects will fix the positioning | 2017-04-13 | 2017-03-23
Creating Coils | Jake, Rence, Chris | Complete | High | 100% | Make Copper Coils for the magnets | 3/14/17 - Wires Expensive, need to find a cheaper place 4/13/17 - Created, looking for new cores | 2017-04-13 | 2017-03-28
Research Magnets | Jake, Rence, Chris | Complete | High | 30% | Buy Magnets and Test them | 3/14/17 - Waiting for Magnets to come in 4/13/17 - Magnets Recieved and testing with the Hall Effect Sensors | 2017-04-13 | 2017-03-28
Buy Adafruit Inductive Power Transfer, IRDATranciever | Andres | Complete | Medium | 100% | Research and buy Inductive Power Transfer, IDRA Sensor | 4/13/17 - Scrapping it and focusing on Levitation | 2017-04-13 | 2017-03-20
Small Scale Levitation | Jake, Rence, Chris | Unfinished | High | 0% | Rebuild the leivtation device, for a small scale | 4/13/17 - We are focusing on the full scale model. | 2017-04-13 | 2017-03-31
Order Frosting Material | Leon | Unfinished | Low | 20% | Research and buy a proper Frosting Material for the Globe | 4/13/17 - Expensive Paint, looking for cheap frosting | 2017-04-13 | 2017-03-31